# Project Schedule Report

| Task | Duration | Resources | Cost | Dependencies |
| --- | --- | --- | --- | --- |
| Project Planning | 5 | Project Manager | 2000.0 |  |
| User Authentication Development | 10 | Senior Dev | 5000.0 | T1 |
| Product Catalog Development | 12 | Senior Dev | 6000.0 | T1 |
| Shopping Cart Development | 10 | Senior Dev | 5000.0 | T2, T3 |
| Payment Processing Development | 8 | Senior Dev | 4000.0 | T4 |
| Order Tracking Development | 8 | Senior Dev | 4000.0 | T5 |
| Testing and Quality Assurance | 15 | QA Engineer | 7500.0 | T6 |
| Deployment and Maintenance | 5 | DevOps Engineer | 2500.0 | T7 |